## Instructions
CD-T2 · Change Impact Assessment
Consumer Duty Implementation — Change & Communications
Purpose
This assessment evaluates the impact of Consumer Duty implementation changes on staff, processes, systems, and customers, informing the Communications Plan Template (CD-T2) and change rollout sequencing.
How to use this workbook
1. Complete one row per change (e.g., new process, system change, policy change). 2. Rate the impact on each stakeholder group. 3. Record mitigation/support actions. 4. Review the Summary tab to identify changes requiring the most communication and support effort.
Note
High-impact changes affecting customers directly should always be paired with a customer communication plan, not just an internal one.

## Change Impact Register
CD-T2 · Change Impact Assessment
Rate impact High/Medium/Low across each stakeholder group
Ref | Change Description | Staff Impact | Process Impact | System Impact | Customer Impact | Mitigation / Support Actions | Owner
CIA-01 | New centralised vulnerable customer identification process | High | High | Medium | Medium | Phased rollout with training; pilot with one team before full launch. | [Insert]
CIA-02 | Revised Fair Value Assessment methodology | Medium | High | Low | Low | Workshop for Product Managers; updated templates and worked examples provided. | [Insert]
CIA-03 | New online cancellation journey for legacy products | Low | Medium | High | High | Customer communication ahead of launch; staff briefed to handle queries during transition. | [Insert]
CIA-04 | Updated complaints categorisation for Consumer Duty themes | Medium | Medium | Medium | Low | Update complaints handling procedures and retrain complaints team. | [Insert]