## Instructions
CD-F3 · Priority Matrix & Action Plan
Consumer Duty Implementation — Foundation Phase
Purpose
This tool converts the outputs of the Gap Analysis Framework (CD-F1) and Risk & Impact Assessment (CD-F3) into a single prioritised action plan, using an Impact vs Effort matrix to sequence remediation and feed the Implementation Roadmap (CD-P3).
How to use this workbook
1. List each item (gap or risk) in the Priority Matrix tab, scoring Impact and Effort 1–5 — Priority calculates automatically. 2. Review the Priority Grid tab, which plots every item automatically (Effort on X axis, Impact on Y axis). 3. Transfer prioritised items into the Action Plan tab with owner, milestones, and target dates. 4. Track status through to completion; RAG calculates from status and target date.
Priority logic
Quick Win (high impact, low effort) — sequence first. Major Project (high impact, high effort) — sequence with adequate resourcing and governance. Fill-In (low impact, low effort) — opportunistic, lower sequencing priority. Deprioritise (low impact, high effort) — reassess necessity before committing resource.

## Summary
CD-F3 · Priority & Action Summary
Auto-calculates from the Priority Matrix and Action Plan
By Priority Quadrant
Quadrant | Count
Quick Win | 1
Major Project | 4
Fill-In | 2
Deprioritise | 1
By Action Status
Status | Count
Not Started | 0
In Progress | 0
Blocked | 0
Complete | 0
Quick Wins should be sequenced first; Major Projects feed the Implementation Roadmap (CD-P3) and Resource Allocation Plan (CD-P3).

## Priority Matrix
CD-F3 · Impact vs Effort Priority Matrix
Score Impact and Effort 1 (Low) to 5 (High) — Priority calculates automatically
Ref | Source Ref (Gap/Risk) | Item Description | Outcome / Area | Impact (1-5) | Effort (1-5) | Priority | Owner
PRI-01 | CD-GAP-01 | Standardise the Fair Value Assessment framework across all products. | Price and Value | 5 | 3 | Major Project
PRI-02 | CD-GAP-02 | Build a consolidated Consumer Duty outcomes MI pack for the Board. | Governance and MI | 5 | 3 | Major Project
PRI-03 | CD-GAP-03 | Implement a centralised vulnerable customer identification process. | Consumer Support | 5 | 4 | Major Project
PRI-04 | CD-GAP-04 | Standardise foreseeable harm assessment in product approval. | Products and Services | 4 | 2 | Quick Win
PRI-05 | CD-GAP-07 | Introduce real-time distribution monitoring against target market. | Products and Services | 3 | 4 | Deprioritise
PRI-06 | CD-GAP-09 | Introduce readability and comprehension testing for communications. | Consumer Understanding | 3 | 2 | Fill-In
PRI-07 | CD-GAP-12 | Remove barriers to switching/cancelling identified in the sludge audit. | Consumer Support | 4 | 3 | Major Project
PRI-08 | CD-GAP-05 | Document how the firm supports customers' financial objectives. | Cross-Cutting Rules | 3 | 2 | Fill-In

## Priority Grid
CD-F3 · Impact / Effort Grid
Auto-plots every item from the Priority Matrix — Effort (X axis) vs Impact (Y axis)
Item | Effort (X) | Impact (Y)
Standardise the Fair Value Assessment framework across all products. | 3 | 5
Build a consolidated Consumer Duty outcomes MI pack for the Board. | 3 | 5
Implement a centralised vulnerable customer identification process. | 4 | 5
Standardise foreseeable harm assessment in product approval. | 2 | 4
Introduce real-time distribution monitoring against target market. | 4 | 3
Introduce readability and comprehension testing for communications. | 2 | 3
Remove barriers to switching/cancelling identified in the sludge audit. | 3 | 4
Document how the firm supports customers' financial objectives. | 2 | 3
Quadrants (informal): top-left = Quick Win · top-right = Major Project · bottom-left = Fill-In · bottom-right = Deprioritise.

## Action Plan
CD-F3 · Action Plan Tracker
Sequenced actions from the Priority Matrix, tracked through to completion
Ref | Priority Ref | Action | Owner | Start Date | Target Date | Status | RAG
ACT-01
ACT-02
ACT-03
ACT-04
ACT-05
ACT-06
ACT-07
ACT-08
ACT-09
ACT-10
ACT-11
ACT-12
ACT-13
ACT-14
ACT-15
ACT-16
Formulas:
RAG = IF([Status]="","",IF([Status]="Complete","Green",IF([Status]="Blocked","Red",IF(AND([Target Date]<>"",[Target Date]<TODAY(),[Status]<>"Complete"),"Red","Amber"))))