## Instructions
CD-M2 · Issue Remediation Tracker
Consumer Duty Implementation — Monitoring & Assurance
Purpose
This tracker manages issues identified through outcome testing, control testing, complaints, or audit through to full remediation, providing an auditable record for the Consumer Duty Oversight Committee and, where relevant, the FCA.
How to use this workbook
1. Log every issue requiring remediation, linked to its source (e.g., Outcome Testing Results Ref, Gap Ref). 2. Record the remediation plan, owner, and target date. 3. Update Status as remediation progresses — RAG calculates automatically from status and date. 4. Confirm customer redress status separately where applicable.
Note
Where remediation involves customer redress, cross-reference the firm's complaints and redress policies; this tracker records the remediation action, not individual customer payments.

## Summary
CD-M2 · Remediation Summary
Auto-calculates from the Remediation Tracker
Category | Count
Not Started | 1
In Progress | 2
Blocked | 0
Complete | 0
Blocked or overdue items should be escalated per the Escalation Pathway Document (CD-P1).

## Remediation Tracker
CD-M2 · Issue Remediation Tracker
Status and date drive RAG automatically
Ref | Source Ref | Issue Description | Root Cause | Remediation Plan | Redress Required? | Owner | Target Date | Status | RAG
REM-01 | OT-02 | Claims handling exceeded SLA without adequate customer communication. | Claims team understaffed; no automated SLA breach alerts. | Implement SLA monitoring dashboard and automated customer updates. | Yes | [Insert] | 2026-06-30 | In Progress | Amber
REM-02 | OT-04 | Online cancellation unavailable for 3 of 5 products. | Digital self-service journeys not built for legacy products. | Build online cancellation journeys for affected products. | No | [Insert] | 2026-09-30 | Not Started | Amber
REM-03 | CD-GAP-03 | No centralised vulnerable customer identification process. | No systematic flagging mechanism across channels. | Deploy Identification Model Specification (CD-I5) across all channels. | No | [Insert] | 2026-07-31 | In Progress | Amber
Formulas:
RAG = IF([Status]="Complete","Green",IF([Status]="Blocked","Red",IF(AND([Target Date]<>"",[Target Date]<TODAY(),[Status]<>"Complete"),"Red","Amber")))