## Instructions
CD-I2 · FVA Review Schedule & Tracker
Consumer Duty Implementation — Price & Value Outcome
Purpose
This tracker schedules and monitors Fair Value Assessments across the product suite on a risk-based cycle, ensuring no product's FVA becomes overdue and providing an auditable record for governance and regulatory review, per the Fair Value Assessment Framework (CD-I2).
How to use this workbook
1. Complete one row per product in the FVA Schedule. 2. Select the Risk Category — this determines the default Review Frequency. 3. Enter the Last FVA Date; the Next FVA Due date and Days Remaining calculate automatically. 4. RAG status calculates automatically based on how close the product is to its due date. 5. Update the Status column as each review is completed.
Review frequency by risk category
High Risk — 12 months. Medium Risk — 18 months. Low Risk — 36 months. RAG thresholds: Red = overdue or due within 30 days; Amber = due within 90 days; Green = more than 90 days until due.

## Summary
CD-I2 · FVA Schedule Summary
Auto-calculates from the FVA Schedule
RAG Status | Count
Red | 1
Amber | 0
Green | 4
Products showing Red should be prioritised immediately and reported to the Product Governance Committee.

## FVA Schedule
CD-I2 · FVA Review Schedule & Tracker
Next due date and RAG calculate automatically from risk category and last review date
Ref | Product / Service | Risk Category | Review Frequency (months) | Last FVA Date | Next FVA Due | Days Remaining | Status | RAG
FVA-01 | Instant Access Savings Account | Medium | 18 | 2025-09-15 | 2027-03-15 | 222 | Complete | Green
FVA-02 | Fixed Term Personal Loan | High | 12 | 2025-11-01 | 2026-11-01 | 88 | Complete | Green
FVA-03 | Stocks & Shares ISA | High | 12 | 2025-02-10 | 2026-02-10 | -176 | Overdue | Red
FVA-04 | Travel Insurance (Single Trip) | High | 12 | 2025-12-01 | 2026-12-01 | 118 | In Progress | Green
FVA-05 | Home Insurance | Medium | 18 | 2025-06-20 | 2026-12-20 | 137 | Complete | Green
Formulas:
Next FVA Due = IF(OR([Last FVA Date]="",[Review Frequency (months)]=""),"",EDATE([Last FVA Date],[Review Frequency (months)]))
Days Remaining = IF([Next FVA Due]="","",[Next FVA Due]-TODAY())