## Instructions
CD-T2 · Communications Plan Template
Consumer Duty Implementation — Change & Communications
Purpose
This plan schedules internal and external communications supporting Consumer Duty implementation changes, ensuring every affected audience receives the right message at the right time, informed by the Change Impact Assessment (CD-T2).
How to use this workbook
1. Complete one row per communication. 2. Link to the relevant Change Impact Assessment Ref where applicable. 3. Track delivery status. 4. Review the Summary tab for upcoming and overdue communications.
Note
For customer-facing communications, apply the Plain Language Checklist (CD-I3) and, where the audience includes vulnerable customers, the Accessible Communications Checklist (CD-I5), before sending.

## Summary
CD-T2 · Communications Summary
Auto-calculates from the Communications Plan
Category | Count
Not Started | 2
In Progress | 1
Complete | 1
Review upcoming communications monthly to ensure timely delivery ahead of each change.

## Communications Plan
CD-T2 · Communications Plan
Scheduled communications supporting Consumer Duty implementation
Ref | Linked Change Ref | Audience | Key Message | Channel | Target Date | Status | Owner
COM-01 | CIA-01 | All customer-facing staff | New vulnerable customer identification process launching; training required beforehand | Email + Team Briefing | 2026-04-15 | In Progress | [Insert]
COM-02 | CIA-03 | Affected customers (legacy products) | New online cancellation option now available | Letter/Email | 2026-06-01 | Not Started | [Insert]
COM-03 | CIA-02 | Product Managers | Revised Fair Value Assessment methodology — workshop invitation | Email + Workshop | 2026-03-20 | Complete | [Insert]
COM-04 |  | Board | Quarterly Consumer Duty progress update | Board Paper | 2026-06-30 | Not Started | [Insert]