## Instructions
CD-P3 · Implementation Roadmap
Consumer Duty Implementation — Programme Delivery
Purpose
This roadmap sequences the workstreams and milestones required to embed Consumer Duty across the firm, consolidating outputs from the Gap Analysis Framework (CD-F1) and Priority Matrix & Action Plan (CD-F3) into a single delivery timeline.
How to use this workbook
1. Complete one row per workstream/milestone in the Roadmap tab. 2. Enter Start and End dates — the Gantt tab shading updates automatically to reflect the monthly view. 3. Update % Complete and Status as delivery progresses. 4. Review the Gantt tab for an at-a-glance view of programme timing and overlaps.
Note
The Gantt view covers a 12-month rolling window from the programme start date entered in cell B3 of the Gantt tab. Adjust this date to re-baseline the view.

## Roadmap
CD-P3 · Implementation Roadmap
Workstreams and milestones — feeds the Gantt view automatically
Ref | Workstream | Milestone / Deliverable | Start Date | End Date | % Complete | Status | Owner
RM-01 | Foundation | Complete Current State Maturity Assessment (CD-F1) | 2026-01-05 | 2026-02-13 | 100% | Complete
RM-02 | Foundation | Complete Gap Analysis & Priority Matrix (CD-F1/F3) | 2026-02-16 | 2026-03-27 | 100% | Complete
RM-03 | Governance | Establish Consumer Duty Oversight Committee (CD-P1) | 2026-01-19 | 2026-02-27 | 90% | On Track
RM-04 | Governance | Approve RACI and Decision Authority Matrices (CD-P1) | 2026-03-02 | 2026-03-20 | 50% | In Progress
RM-05 | Products & Services | Complete target market definitions for all products (CD-I1) | 2026-03-02 | 2026-05-01 | 40% | On Track
RM-06 | Price & Value | Roll out Fair Value Assessment Framework (CD-I2) | 2026-04-06 | 2026-06-26 | 10% | Not Started
RM-07 | Consumer Understanding | Implement communication testing protocol (CD-I3) | 2026-05-04 | 2026-07-31 | 0% | Not Started
RM-08 | Consumer Support | Deploy vulnerable customer identification model (CD-I5) | 2026-06-01 | 2026-09-25 | 0% | Not Started
RM-09 | Monitoring | Build Consumer Duty outcomes MI dashboard (CD-M1) | 2026-07-06 | 2026-09-11 | 0% | Not Started
RM-10 | Training | Deliver role-based Consumer Duty training (CD-T1) | 2026-08-03 | 2026-10-30 | 0% | Not Started
RM-11 | Governance | Prepare first Annual Consumer Duty Board Report (CD-M3) | 2026-10-05 | 2026-12-18 | 0% | Not Started

## Gantt View
CD-P3 · Roadmap Gantt View
Monthly view auto-shaded from Start/End dates in the Roadmap tab
Programme Start | 2026-01-01
Milestone | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Complete Current State Maturity Assessment (CD-F1)
Complete Gap Analysis & Priority Matrix (CD-F1/F3)
Establish Consumer Duty Oversight Committee (CD-P1)
Approve RACI and Decision Authority Matrices (CD-P1)
Complete target market definitions for all products (CD-I1)
Roll out Fair Value Assessment Framework (CD-I2)
Implement communication testing protocol (CD-I3)
Deploy vulnerable customer identification model (CD-I5)
Build Consumer Duty outcomes MI dashboard (CD-M1)
Deliver role-based Consumer Duty training (CD-T1)
Prepare first Annual Consumer Duty Board Report (CD-M3)
Blue shading indicates the milestone is active during that month, calculated from the Start/End dates in the Roadmap tab.