## Instructions
CD-P3 · Resource Allocation Plan
Consumer Duty Implementation — Programme Delivery
Purpose
This plan allocates people resource (FTE) to each Consumer Duty workstream across the Implementation Roadmap (CD-P3), identifying over- or under-resourced areas before delivery begins.
How to use this workbook
1. List each workstream and the roles/functions contributing to it. 2. Enter Allocated FTE and Required FTE for each row — the Variance calculates automatically. 3. Review the Summary tab for total resource demand vs capacity by function. 4. Update monthly as the programme progresses and priorities shift.
Note
FTE (full-time equivalent) should reflect the proportion of a role's capacity dedicated to this workstream, not headcount — e.g., 0.2 FTE means one-fifth of one person's time.

## Summary
CD-P3 · Resource Summary
Auto-calculates from the Resource Allocation Plan
Metric | Value
Total Allocated FTE | 4.6
Total Required FTE | 7
Overall FTE Gap | -2.4
Workstreams Under-Resourced | 7
Under-resourced workstreams should be flagged to the Consumer Duty Oversight Committee and reflected in the Implementation Roadmap (CD-P3).

## Resource Allocation
CD-P3 · Resource Allocation Plan
Allocated vs required FTE by workstream and function — variance calculates automatically
Ref | Workstream | Function / Role | Allocated FTE | Required FTE | Variance | Risk if Unresourced | Owner
RES-01 | Foundation | Compliance | 0.6 | 0.5 | 0.1 | Low — assessment phase largely complete.
RES-02 | Governance | Company Secretariat | 0.3 | 0.4 | -0.1 | Medium — committee papers may slip without additional support.
RES-03 | Products & Services | Product Management | 1.2 | 2 | -0.8 | High — target market work across 30+ products cannot complete on time.
RES-04 | Price & Value | Pricing/Actuarial | 0.5 | 1 | -0.5 | High — FVA refresh for high-risk products will be delayed.
RES-05 | Consumer Understanding | Marketing/Design | 0.4 | 0.6 | -0.2 | Medium — communication testing timeline at risk.
RES-06 | Consumer Support | Customer Operations | 0.8 | 1 | -0.2 | Medium — vulnerable customer rollout may need to phase.
RES-07 | Monitoring | Data & MI | 0.5 | 1 | -0.5 | High — outcomes dashboard build will slip without additional analyst support.
RES-08 | Training | Learning & Development | 0.3 | 0.5 | -0.2 | Medium — role-based training content development slower than planned.