## Instructions
CD-P3 · Budget Template
Consumer Duty Implementation — Programme Delivery
Purpose
This template tracks budgeted vs actual spend for the Consumer Duty implementation programme by workstream and cost category, supporting the Implementation Roadmap (CD-P3) and Resource Allocation Plan (CD-P3).
How to use this workbook
1. Complete one row per budget line in the Budget Tracker. 2. Enter the Budgeted amount and update Actual Spend to Date monthly. 3. Variance and % Utilised calculate automatically. 4. Review the Summary tab for total programme spend against budget.
Cost categories
People — internal staff time and contractor/consultant costs. Technology — system builds, MI dashboards, data tooling. Training — content development and delivery. External Advisory — legal, regulatory, or specialist consultancy. Other — printing, communications, miscellaneous.

## Summary
CD-P3 · Budget Summary by Category
Auto-calculates from the Budget Tracker
Cost Category | Total Budgeted (£)
People | 165000
Technology | 240000
Training | 35000
External Advisory | 70000
Other | 15000
Budget lines showing over 100% utilisation should be escalated immediately to the programme sponsor.

## Budget Tracker
CD-P3 · Budget Tracker
Budgeted vs actual spend by workstream — variance and utilisation calculate automatically
Ref | Workstream | Cost Category | Budgeted (£) | Actual Spend to Date (£) | Variance (£) | % Utilised | Owner
BUD-01 | Foundation | People | 45000 | 44000 | 1000 | 97.78%
BUD-02 | Governance | External Advisory | 30000 | 18000 | 12000 | 60%
BUD-03 | Products & Services | People | 120000 | 55000 | 65000 | 45.83%
BUD-04 | Price & Value | Technology | 60000 | 12000 | 48000 | 20%
BUD-05 | Consumer Understanding | External Advisory | 40000 | 5000 | 35000 | 12.5%
BUD-06 | Consumer Support | Technology | 85000 | 8000 | 77000 | 9.412%
BUD-07 | Monitoring | Technology | 95000 | 15000 | 80000 | 15.79%
BUD-08 | Training | Training | 35000 | 2000 | 33000 | 5.714%
BUD-09 | Programme-wide | Other | 15000 | 4000 | 11000 | 26.67%
| TOTAL |  | 525000 | 163000 | 362000 | 31.05%